# PRT661- Dan5 - Meeting Minutes 02

| Location: | Online Meeting via Teams |
| --- | --- |
| Date: | 06/08/2026 |
| Time: | 09:00PM - 10:30PM |
| Attendees: | Huynh Anh Thi Pham Dieu Yen Diep Lihini Jinanjalie Deniyelge Navodya Piumanthi Siriwardhana Senarath Mudiyanselage |

# Progress from last meetings

| # Action items | # Owner(s) | # Deadline | # Status |
| --- | --- | --- | --- |
| Review Assessment 1 requirements and rubric | All members | 06/08/2026 | Completed |
| Explore potential project topics and datasets | All members | 06/08/2026 | Completed |
| Identify potential data sources for the proposed project | All members | 06/08/2026 | Completed |

# Discussion Point

The group discussed and clarified the Assessment 1 rubric and submission requirements, particularly the expectations regarding project feasibility, Theme 2 alignment, data acquisition, architecture, workflow, and evidence of collaboration.

The group discussed whether the proposed project should remain focused on the original topic or consider alternative project directions based on dataset availability and project feasibility.

Several potential datasets were reviewed and compared based on:

- Relevance to the proposed problem.

- Availability and accessibility.

- Dataset size and coverage.

- Suitability for predictive analytics and machine learning.

- Reliability of the data source.

The group discussed potential missing-value issues identified in the available datasets. Members agreed that the extent and pattern of missing data should be documented as an initial project risk rather than deciding on detailed data-processing methods at this proposal stage.

The group discussed the importance of demonstrating a clear real-world problem and explaining why the proposed predictive solution would provide practical value.

The group agreed to divide the Assessment 1 preparation tasks among members so that each member has a clearly defined responsibility.

| # Action items | # Owner(s) | # Deadline | # Status |
| --- | --- | --- | --- |
| Confirm the most suitable dataset for the proposed project | All members | 09/08/2026 | In progress |
| Document dataset sources and availability | All members | 09/08/2026 | In progress |
| Assign tasks for group members | All members | 11/08/2026 | In progress |
| Develop the initial architecture diagram | All members | 11/08/2026 | In progress |
| Develop the initial workflow plan | All members | 11/08/2026 | In progress |
| Review the Assessment 1 report and ensure all required sections are covered | All members | 11/08/2026 | In progress |

# Next meeting time and venue

Date: Around 11/08/2026

Time: After 8:00PM
Venue: Online