# PRT661- Dan5 - Meeting Minutes 04

| Location: | Online Meeting via Teams |
| --- | --- |
| Date: | 27/08/2026 |
| Time: | 15:00PM - 16:00PM |
| Attendees: | Huynh Anh Thi Pham Dieu Yen Diep Lihini Jinanjalie Deniyelge Navodya Piumanthi Siriwardhana Senarath Mudiyanselage Favour Ikponwosa Esangbedo |

# Progress from last meetings

| # Action items | # Owner(s) | # Deadline | # Status |
| --- | --- | --- | --- |
| Read and review other members' sections | All members | 15/08/2026 | In progress |
| Provide comments and identify mistakes or inconsistencies | All members | 15/08/2026 | In progress |
| Add individual names to the appropriate contribution/task section | All members | 15/08/2026 | In progress |
| Add Group ID, Unit ID and Unit Name to the footer | All members | 15/08/2026 | In progress |
| Conduct a final review of the complete report | All members | 15/08/2026 | In progress |

# Discussion Point

Dashboard design and output requirements: Discussed developing a simple web-based dashboard to present today's air-quality conditions, next-day PM₂.₅ predictions and fire locations within Greater Darwin.

Dashboard development approach: Agreed that the dashboard should remain simple and practical due to the project timeframe. The team discussed the need to clarify the appropriate dashboard development tool and whether a third-party dashboard platform can be used.

AWS learning activities and project requirements: Discussed whether the AWS activities are required for the assessment or mainly provided as learning/tutorial support. The team agreed that this should be clarified with the lecturer/tutor before proceeding.

Project task allocation and next steps: Reviewed the current task allocation and agreed to continue with the proposed allocation. Discussed completing the remaining work as soon as possible and confirming dashboard requirements and AWS expectations.

Discussed the findings and data analysis techniques relevant to our study.

Discuss the individual progress of AWS Lab.

| # Action items | # Owner(s) | # Deadline | # Status |
| --- | --- | --- | --- |
| Confirm the requirements and appropriate tool/platform for the web dashboard | All members | Before next meeting | In progress |
| Clarify with the lecturer/tutor whether AWS activities are required for the assessment | All members | Before next meeting | In progress |
| Continue completing assigned project tasks according to the current task allocation | All members | Before next meeting | In progress |
| Finalise the dashboard concept and determine the main information to display | All members | Before next meeting | In progress |

# Next meeting time and venue

Date: Around 29/08/2026

Time: After 8:00PM
Venue: Online